## product backlog
PRODUCT BACKLOG ID | PRIORITY | USER STORY ID | user stories | scrum team assigned | status | remark
sprint 1
PB-1 | high | user001 | Account Management | Arupa and vaishali team | completed
sprint 2
PB-2 | medium | user002 | Fund Transfer | Shahbaz Team | completed
PB-3 | high | user003 | Bill Payments | Sathish Team | In progress
sprint 3
PB-4 | medium | user004 | Loan Service | Tanya | In progress
sprint 4
PB-5 | high | user005 | Notification | Swanand | Testing
sprint 5
PB-6 | medium | user006 | Customer Support | Nilima and anusha team | completed

## sprint backlog 1
USER STORY ID | USER STORY NAME | USER STORY STEP DEFINITION |  |  | ASSIGNED TO | ESTIMATED TIME | ACTUAL TIME | STATUS | REMARKS
|  | AS A<type of user> | I WANT TO <perform some task> | SO THAT I CAN <achieve some goal>
USER001 | Account Management | as a user , | Secure login to account | see the information about account | satish | 3 hr | 2hr | completed
| Funds Transfer | as a user | Transfer funds to another account | manage my finances | shahbaz | 5hr | 3hr | In progress
| bill payments | as a user | pay the bills directly from the bank accounts | so that it can payed | tanya | 4hr | 2hr | completed
| Loan services | as a user | apply for the loans | so that user can get loan | swanand | 3hr | 3hr | completed
|  | as a admin | grant the loan | so that admin can grant the loan | anusha | 4hr | 3hr | In progress
| Notifications | as a admin | send the notification for due payments etc. | so that user can get important messege | arupa | 4hr | 4hr | Testing
| Customer support | as a user | can get live chat and messeging | so that user get banking services | vaishali | 5hr | 4hr | In progress
|  | as a admin | provide solution to the user quries

## spring backlog 2
s.no | userstories | user story step | assigned to | estimated hour | status | remark
| call | if network is avialabe it can make calls,
switch to audio video model,

## sprint 3
Backlog | To Do | In Progress | Testing | Done
|  | PB-3 | PB-5 | PB-1
|  | PB-4 |  | PB-2
PB-6